## 1 Mar 19
Chosen Start Date: 1 March 2019
S/N | Research Milestone | Fiscal Year | Start Date | End Date
1 | Chip demonstration of low-level scene analysis building blocks - Integrated circuit performing feature extraction at 50 µW power (or lower) at VGA resolution, 5fps frame rate | FY2021 | 2019-03-01 | 2021-08-31
2 | Chip demonstration of low-level scene analysis building blocks - Integrated circuit performing feature extraction at 50 µW power (or lower) at VGA resolution, 5fps frame rate | FY2021 | 2019-03-01 | 2021-08-31
3 | Chip demonstration of low-level scene analysis building blocks - Imager with 100 µW power (VGA, 30 fps) at activity rate of average NeoVision2 benchmark | FY2021 | 2019-03-01 | 2021-08-31
4 | Deep learning model with reduced complexity - 1,000X reduced size with <2% accuracy degradation in object and human detection, compared to deep learning network with best-in-class accuracy (e.g., 63.7% according to MobilNet baseline, based on ImageNet benchmark) | FY2021 | 2019-03-01 | 2021-08-31
5 | System on chip demonstration of a complete cognitive camera - Integrated circuit performing image sensing and scene analysis with average power consumption in the mW range, including neural acceleration with maximum accuracy no lower than the best-in-class detection/classification algorithms minus 5-10% (indoor, 500-lux lighting, max. 20 people) | FY2023 | 2019-03-01 | 2024-02-29

## 1 Apr 19
Chosen Start Date: 1 April 2019
S/N | Research Milestone | Fiscal Year | Start Date | End Date
1 | Chip demonstration of low-level scene analysis building blocks - Integrated circuit performing feature extraction at 50 µW power (or lower) at VGA resolution, 5fps frame rate | FY2021 | 2019-04-01 | 2021-09-30
2 | Chip demonstration of low-level scene analysis building blocks - Integrated circuit performing feature extraction at 50 µW power (or lower) at VGA resolution, 5fps frame rate | FY2021 | 2019-04-01 | 2021-09-30
3 | Chip demonstration of low-level scene analysis building blocks - Imager with 100 µW power (VGA, 30 fps) at activity rate of average NeoVision2 benchmark | FY2021 | 2019-04-01 | 2021-09-30
4 | Deep learning model with reduced complexity - 1,000X reduced size with <2% accuracy degradation in object and human detection, compared to deep learning network with best-in-class accuracy (e.g., 63.7% according to MobilNet baseline, based on ImageNet benchmark) | FY2021 | 2019-04-01 | 2021-09-30
5 | System on chip demonstration of a complete cognitive camera - Integrated circuit performing image sensing and scene analysis with average power consumption in the mW range, including neural acceleration with maximum accuracy no lower than the best-in-class detection/classification algorithms minus 5-10% (indoor, 500-lux lighting, max. 20 people) | FY2023 | 2019-04-01 | 2024-03-31

## 1 May 19
Chosen Start Date: 1 May 2019
S/N | Research Milestone | Fiscal Year | Start Date | End Date
1 | Chip demonstration of low-level scene analysis building blocks - Integrated circuit performing feature extraction at 50 µW power (or lower) at VGA resolution, 5fps frame rate | FY2021 | 2019-05-01 | 2021-10-31
2 | Chip demonstration of low-level scene analysis building blocks - Integrated circuit performing feature extraction at 50 µW power (or lower) at VGA resolution, 5fps frame rate | FY2021 | 2019-05-01 | 2021-10-31
3 | Chip demonstration of low-level scene analysis building blocks - Imager with 100 µW power (VGA, 30 fps) at activity rate of average NeoVision2 benchmark | FY2021 | 2019-05-01 | 2021-10-31
4 | Deep learning model with reduced complexity - 1,000X reduced size with <2% accuracy degradation in object and human detection, compared to deep learning network with best-in-class accuracy (e.g., 63.7% according to MobilNet baseline, based on ImageNet benchmark) | FY2021 | 2019-05-01 | 2021-10-31
5 | System on chip demonstration of a complete cognitive camera - Integrated circuit performing image sensing and scene analysis with average power consumption in the mW range, including neural acceleration with maximum accuracy no lower than the best-in-class detection/classification algorithms minus 5-10% (indoor, 500-lux lighting, max. 20 people) | FY2023 | 2019-05-01 | 2024-04-30